## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Green
Wood Furniture Design Customization and Ordering System
Gil's Furniture Shop
Team Members
Reyes, Glydel Ann E.
Comia, Juriel U.
Ramos, John Kyle C.
Project end date: | 2022-10-21
Milestone description | Progress | Missing
Login/Sign Up, DB Connection and Design
Landing Page | 50% | Products display in landing page
DB Connection/Signup and Login | 100% | None
Design and Adding of Data/Product (Admin Only) | 100% | None
Select Product Category and Search | 100% | None
Display Transaction Page | 100% | None
Message and Furniture Progress
Message Page Design | 50% | Working progress
User and Admin Profile Page | 100% | None
Update Profile and Product Info | 50% | Update product (Admin only)
Message Transaction for User and Admin | 90% | Upload and send image
Working Progress | 0% | Progress, order details display and deliver
Order Item | 100% | None
User Post | 33% | Comments and image/file upload
Customization Page / Terms of Use, Guidelines and User Privacy
Furniture Customization | 0%
Convertion of Customized Design to Image File | 0%
Terms of Use, Privacy of User | 0%
Responsive Design (User) | 25% | Mobile, tablet, laptop view
Web/Live Hosting | 0%
Testing
Validation Testing
Unit Testing
Cross-Compatibility Test
52.82%

## Blue
Project title
Company name
Project lead
Project start date: | 2022-10-03 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | October | [20 empty] | November | [27 empty] | December
 | time axis 2022-10-16 to 2022-12-10
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-10-16 to 2022-12-10
Title 1
Task 1 |  | 25% | 2022-10-06 | 3
Task 2 |  |  | 2022-10-11 | 1
Task 3 |  | 50% | 2022-10-03 | 10
Task 4 |  |  | 2022-10-26 | 1 | bar: 2022-10-26
Task 5 |  | 10% | 2022-10-12 | 6
Title 2
Task 1 |  | 60% | 2022-10-12 | 13
Task 2 |  | 50% | 2022-10-13 | 9
Task 3 |  | 33% | 2022-10-21 | 11
Task 4 |  |  | 2022-10-30 | 1 | bar: 2022-10-30
Task 5 |  |  | 2022-10-31 | 24
Title 3
Task 1 |  |  | 2022-10-21 | 4
Task 2 |  |  | 2022-10-25 | 14
Task 3 |  |  | 2022-11-10 | 6
Task 4 |  |  | 2022-11-23 | 3
Task 5 |  |  | 2022-11-15 | 19
Title 4
Task 1 |  |  | 2022-11-12 | 15
Task 2 |  |  | 2022-11-04 | 5
Task 3 |  |  | 2022-12-25 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project title
Company name
Project lead
Project start date: | 2022-10-03 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | October | [20 empty] | November | [27 empty] | December
 | time axis 2022-10-16 to 2022-12-10
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-10-16 to 2022-12-10
Title 1
Task 1 |  | 25% | 2022-10-06 | 3
Task 2 |  |  | 2022-10-11 | 1
Task 3 |  | 50% | 2022-10-03 | 10
Task 4 |  |  | 2022-10-26 | 1 | bar: 2022-10-26
Task 5 |  | 10% | 2022-10-12 | 6
Title 2
Task 1 |  | 60% | 2022-10-12 | 13
Task 2 |  | 50% | 2022-10-13 | 9
Task 3 |  | 33% | 2022-10-21 | 11
Task 4 |  |  | 2022-10-30 | 1 | bar: 2022-10-30
Task 5 |  |  | 2022-10-31 | 24
Title 3
Task 1 |  |  | 2022-10-21 | 4
Task 2 |  |  | 2022-10-25 | 14
Task 3 |  |  | 2022-11-10 | 6
Task 4 |  |  | 2022-11-23 | 3
Task 5 |  |  | 2022-11-15 | 19
Title 4
Task 1 |  |  | 2022-11-12 | 15
Task 2 |  |  | 2022-11-04 | 5
Task 3 |  |  | 2022-12-25 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one